## start here
free run-of-show template
by Brady UX · bradyux.com/tools/run-of-show-template
how to use it
1. Go to the "run of show" tab. Type your event name, date and venue at the top.
2. Replace the example rows with your own. One row per moment of the day, in time order.
3. Pick a status for each row from the dropdown: confirmed, waiting, at risk or done. Rows colour themselves.
4. Fill in the "crew" and "vendors" tabs. The totals at the top of each tab count themselves.
5. Share it with your team as view-only on the day, so there is exactly one version.
the colour key
Cream cells = yours to fill in. Grey cells = formulas that calculate themselves (don't type over them).
The example rows (a Saturday conference) show the format. Delete or overwrite them.
using Google Sheets?
In Google Drive: New > File upload > pick this file > open it > File > Save as Google Sheets. Dropdowns and colours carry over.
outgrown the spreadsheet?
When six versions are floating around and crew are scheduled by group text, a spreadsheet stops being enough.
We turn it into one simple tool your whole team uses, on every phone, in about a week: bradyux.com/tools/events

## run of show
run of show
event | Saturday conference (example) |  |  | crew needed (total)
date | Sat, Nov 14 |  |  | rows confirmed
venue | Main hall |  |  | rows at risk
start | end | mins | what's happening | where | owner | crew needed | vendor / contact | status | notes
7:00 | 9:00 |  | Load-in: tables + staging | Dock B | Sam | 4 | Rental truck · 555-0101 | confirmed | Back gate code 4471
9:30 | 10:30 |  | AV check: sound + projector | Main hall | Priya | 2 | Bright AV · 555-0102 | confirmed
11:00 | 11:30 |  | Catering drop-off | Kitchen | Jordan | 2 | Green Plate Catering · 555-0103 | waiting | Needs final headcount by Thu
12:30 | 13:00 |  | Check-in table set up | Lobby | Sam | 3 |  | waiting | Badges + lanyards in box 3
13:00 | 13:15 |  | Doors open | Lobby | Priya | 3 |  | at risk | 1 crew short
13:15 | 14:00 |  | Welcome + keynote | Main stage | Alex | 1 | Speaker: on site 12:30 | confirmed | Clicker + water on lectern
17:00 | 19:00 |  | Teardown | Main hall | Sam | 5 | Rental truck · 555-0101 | waiting | Truck back at 7pm

## crew
crew
people
confirmed
name | role | phone | shift start | shift end | hours | confirmed | notes
Sam | Lead / load-in | 555-0111 | 7:00 | 19:00 |  | yes
Priya | Doors + AV | 555-0112 | 9:00 | 17:00 |  | yes
Jordan | Catering + green room | 555-0113 | 10:30 | 16:00 |  | no | Confirm by Thu
Alex | Stage manager | 555-0114 | 12:00 | 18:00 |  | yes

## vendors
vendors
vendors
confirmed
paid
vendor | providing | contact | phone | arrives | load-in spot | confirmed | paid | notes
Rental truck | Tables, chairs, staging | Dana | 555-0101 | 7:00 | Dock B | yes | no | Deposit paid, balance on day
Bright AV | Sound + projector | Chris | 555-0102 | 9:30 | Dock B | yes | yes
Green Plate Catering | Lunch for 120 | Maya | 555-0103 | 11:00 | Kitchen door | no | no | Final headcount due Thu